Java Team Project - Team Organization and Task Assignment Sheet

Project Title: Out-N-In Management System

_____________________________________________________________________________________

Team Members:

- Team Lead: Wacim HAMDI

- Developer 1: Pablo BIRAN

- Developer 2: Aaron JEHCHI

- Developer 3: Sacha LEVI

- Developer 4: Camille PICOU

_____________________________________________________________________________________

Project Description:

Out-n-In Management System is a Java application designed to manage the daily operations of a fictional restaurant named “Out-n-In”. Its main objective is to centralize the handling of three core areas of the business (food stock, staff and subscribed customers, and menus) within a single, easy-to-use program, while putting into practice the fundamentals of Java development. The application provides a graphical interface built with Java Swing, through which users can display, add, modify, and delete one or several entities at once in each area. The project is built on object-oriented programming principles, with clearly structured classes modeling each entity, and it relies on a SQL database queried from Java to store and retrieve data persistently. Robust exception handling ensures that errors, such as invalid inputs or failed database operations, are caught and reported clearly to the user rather than crashing the program.

_____________________________________________________________________________________

Task Assignment:

Team Lead : Wacim HAMDI

Responsibilities:

- Leads the group: keeps the task list up to date, runs the weekly meeting and the sprint reviews, and decides what stays in or out of the project.

- Owns everything related to the database: how the information is organised, and how the Java program reads and writes it.

- Reviews the work of the others before it is added to the shared version of the project.

- Makes sure the deadlines are met and helps whoever is stuck. Reference person for any database question.

Tasks:

T1 - Design the database

- Decide which tables are needed (ingredients, employees, customers, subscriptions, dishes, menus) and how they are linked together.

- Write the scripts that create these tables and fill them with realistic test data, so that every screen has something to display.

T2 - Connect the application to the database

- Write the part of the program that opens the connection, with the address and the password kept in a settings file so that each member can use their own local database.

- Write a short installation guide so that anyone in the group can set the database up alone.

T3 - Write the database operations

- Define the set of operations every type of record needs: list, search, add, update, delete, and delete several at once. This set is the model Camille follows on her side.

- Write these operations for ingredients, dishes and menus.

- Make sure a failed operation never leaves the database half updated.

T4 - Add the searches and filters

- Provide what the screens need to display: ingredients running low, dishes by category or by price, menus containing a given dish, subscriptions still valid or expired.

- Make sure a database problem is always turned into a clear message instead of a technical error shown to the user.

Developer 1 : Pablo BIRAN

Responsibilities:

- Owns the GitHub repository: how it is organised, how everyone adds their work to it, and the versions that are released. Reference person for any Git problem.

- Owns error handling: the family of errors used across the project and the way they are shown to the user.

- Draws the UML diagrams and keeps them up to date for the report and the presentation.

- Puts the slide deck together and organises the rehearsal session.

Tasks:

T5 - Set up and maintain the repository

- Create the repository, give each member their own working branch, and write down the few rules everyone follows to add their work to the shared version.

- Write the README explaining what the project is, how to compile it and how to run it.

- Save a version at the end of each sprint, so a working version is always available.

T6 - Design the error handling

- Create the family of errors used everywhere in the project: invalid input, database problem, record not found, not enough stock, duplicate entry.

- Write down the rule the team follows: where an error is raised, and where it is caught and displayed. Nobody invents their own way of handling errors.

- Make sure an unexpected error is recorded in a log file instead of closing the window without explanation.

T7 - Provide the shared checking and error tools

- Write the checks used by every form: empty field, number, price, date, duplicate name.

- Write the single error window that the whole team calls, so that error messages look the same in every screen. Sacha and Camille use it instead of writing their own.

T8 - Diagrams, slide deck and presentation

- Produce the class diagram, the use case diagram and the diagram of the database.

- Build the slide deck: goal of the project, how the program is organised, live demonstration, error handling, division of the work, difficulties met.

- Write the demonstration script (what is shown, in which order, by whom) and organise the rehearsal session on Sunday 18 October.

Developer 2: Aaron JEHCHI

Responsibilities:

- Owns the Java classes that represent the restaurant: ingredients, dishes, menus, employees, customers and subscriptions. This is the object-oriented heart of the project.

- Owns the rules of the restaurant: what is allowed, what is refused, and what is calculated.

- Delivers his classes first, during week 1, because the whole group builds on them; any later change is announced to the group before it is made.

- Writes the tests proving the rules work, and backs up whoever is late during the last week.

Tasks:

T9 - Write the classes of the restaurant (priority: week 1)

- A common class for people, extended by employees and by customers - this is where inheritance is demonstrated.

- The classes for ingredients, dishes, menus and subscriptions, with the information each one holds.

- Keep these classes free of any database or interface code, so that they can be used by everyone without side effects.

T10 - Rules about stock and menus

- Tell whether a dish can be prepared with the stock available, and refuse it clearly when it cannot.

- Remove the ingredients used when a dish is prepared, and list what is running low.

- Calculate the price of a menu and refuse a menu that contains an unavailable dish.

T11 - Rules about employees and subscribed customers

- Adding, updating and removing an employee, with simple checks such as a salary that cannot be negative.

- Tell whether a subscription is still valid or expired, allow renewing it, and apply the discount given to subscribers.

T12 - Tests and demonstration data

- Write tests for each rule: the case that works and the case that must be refused.

- Prepare a small set of data held in memory, so that the screens can be developed and shown even when the database is not available.

Developer 3: Sacha LEVI

Responsibilities:

- Owns the interface: the main window, the navigation between screens, and the building blocks the others reuse.

- His building blocks (table, forms, confirmation window) are the reference. Camille reuses them instead of writing her own, which keeps the application consistent.

- Keeps the screens clean: a screen never talks to the database directly, it goes through the work of Wacim and Aaron.

- Checks that the interface stays comfortable to use on the laptop used for the demonstration, even with long lists.

Tasks:

T13 - Build the main window

- One window with four tabs: Stock, Menus, Employees, Customers.

- Define the common style (fonts, colours, spacing) so that every screen looks like the same application.

T14 - Build the reusable blocks (needed early: Camille waits for them)

- A table able to display any list of records, with sortable columns and several rows selectable at once.

- A window to add or edit a record, and a confirmation window for deletions saying how many records are concerned.

T15 - Stock screen

- Display the ingredients, with buttons to add, edit, delete and refresh, and a search field.

- Make the ingredients running low stand out, and allow deleting several of them in one go.

T16 - Dishes and menus screen

- Display dishes and menus side by side, and allow building a menu by choosing dishes, with the resulting price shown.

- Allow editing the recipe of a dish (which ingredients and how much), and show when a dish cannot be prepared.

Developer 4: Camille PICOU

Responsibilities:

- Owns the start-up of the application: it is her part that launches everything in the right order when the program is run.

- Owns the Employees and Customers screens, built with Sacha's blocks.

- Owns the database operations for employees, customers and subscriptions, following the model defined by Wacim.

- Owns the test list and the final check that everything works together before submission.

Tasks:

T17 - Start the application

- Write the starting point of the program: read the settings, open the database, prepare what the screens need, then display the main window.

- If the database cannot be reached, show a clear message explaining what to check instead of a technical error.

- Provide a demonstration mode running on Aaron's in-memory data, kept as a safety net in case the database fails during the presentation.

T18 - Database operations for employees and customers

- Write the list, add, update and delete operations for employees, customers and subscriptions, in exactly the same way as Wacim did for the food side.

- Bring back a customer together with their subscription in a single operation.

T19 - Employees and customers screens

- Employees: list with add, edit and delete (one or several at a time) and a filter by role.

- Customers: list of subscribers showing whether each subscription is still valid or expired, with a button to renew it.

T20 - Test list and final assembly

- Write the list of everything that must be tested and the expected result: add, edit, delete, delete several, wrong input, expired subscription, missing ingredient, database switched off.

- Organise the round where each member tests a part written by somebody else, and write down the bugs found.

- Bring everybody's work together, replay the whole test list, and help Pablo prepare the demonstration.

_____________________________________________________________________________________

Presenter and Slides compiler

Write the presentation and coordinate with team members to practice the presentations

Responsible: Pablo BIRAN (slide deck and main presenter). During the live demonstration, each member presents the part he or she developed.

- Slide deck ready by Friday 16 October, so that everyone can read it before the rehearsal.

- Demonstration script saying who speaks when, what is shown, and which error is triggered on purpose to show how the program reacts.

- Only 1 session of practicing : Sunday 18th October, in the afternoon

_____________________________________________________________________________________

Milestones and Timeline:

Kick-off - Monday 28 September

- Subject read together, scope agreed on the four required areas (Java classes, Swing interface, error handling, SQL database) and roles assigned.

- Two things agreed before splitting up, because everybody depends on them: the classes of the restaurant and the list of database operations.

- Repository created and cloned by the five members the same evening.

Sprint 1 (Week 1): 28 September - 4 October

- Goal of the sprint: an application that starts, even if it does not do anything yet.

- T9 (Aaron) delivered on 1 October: from that moment everyone could work on top of the real classes instead of waiting.

- T1 (Wacim) reviewed during the Thursday meeting, with one change coming out of it - the recipe of a dish became a proper table instead of a simple text field.

- T5 and T6 (Pablo) done on 2 October: repository, branches and the family of errors available to everyone.

- T13 (Sacha) done on 3 October: main window with its four empty tabs, started by T17 (Camille) on temporary data, with no database yet.

- Sprint review on Sunday 4 October: version v0.1 saved - the application opens and the tabs are there, nothing is saved yet, which was expected.

Sprint 2 (Week 2): 5 October - 11 October

- Goal of the sprint: real data in the database, and the first screens able to add, edit and delete records.

- 5 October: database installed by everyone with Wacim's scripts. Two members could not connect to it; solved the same day, and the missing step was added to the installation guide (T2) so that it would not happen again.

- T3 (Wacim) finished on 8 October, T18 (Camille) on 9 October - one day later than planned, because of the link between a customer and their subscription.

- T14 (Sacha) delivered on 7 October, before the rest of his work, because Camille was waiting for it. T15 finished on 9 October.

- T10 and T11 (Aaron) delivered with their first tests: preparing a dish without enough ingredients is now refused instead of giving a negative stock.

- T7 (Pablo) added on 10 October: every screen now uses the shared checks and the shared error window.

- Sprint review on Sunday 11 October: version v0.5 saved - stock and employees fully usable with the database, menus and customers still partly read-only. Decision taken at the review: drop the sales statistics screen mentioned at the kick-off, and finish what is required properly instead.

Sprint 3 (Week 3): 12 October - 18 October

- Goal of the sprint: finish the last screens, test everything, prepare the presentation.

- 12 October: T16 (Sacha) with the recipe editor and T19 (Camille) with the subscription status - the four screens are complete.

- 13 October: deleting several records at once finished on both sides (T3 and T18), and the searches and filters plugged into the screens (T4).

- 14 October: testing round, each member testing a part written by somebody else. Eleven problems found, eight fixed the same evening - a list that did not refresh after a deletion, a crash when clicking Edit without selecting a row, an unclear message when deleting an ingredient still used by a dish, and a price field refusing a comma.

- 15 October: last problems fixed, comments added to the code, README and installation guide completed, UML diagrams finished.

- 16 October (planned): no new feature from now on, version v1.0 saved, and the whole test list replayed on a fresh installation.

- 17 October (planned): slide deck finished, demonstration script written, demonstration mode tested as a backup.

- Sunday 18 October, afternoon (planned): the single rehearsal session - two full run-throughs, timing checked, likely questions prepared.

Finalization (Week 3):

- Integration of all modules: the work of the five members brought together and saved as the final version v1.0.

- Final testing and bug fixing: the test list replayed on a fresh installation with an empty database, so that nothing depends on one particular computer.

- Documentation and project submission: README, installation guide, UML diagrams, test list, slide deck and this organisation sheet.

_____________________________________________________________________________________

Communication Plan:

Weekly Team Meetings:

Every Thursday at 6:00 p.m. (campus room or Discord voice channel): progress, blocking points, plan for the coming days. Short review every Sunday evening at the end of a sprint.

Communication Channels:

Discord server of the group for daily updates and quick questions, with one channel per area (#database, #interface, #errors, #general) and one channel receiving the GitHub notifications.

Email for formal communication.

GitHub for code collaboration and version control.

GitHub Team Project Web Address: [to be completed with the repository URL]

Notes:

- One owner per part. If somebody needs a change in a part owned by another member, he or she asks the owner instead of modifying it directly. This is what keeps conflicts rare.

- Nobody works directly on the final version: each member works on their own branch and asks for their work to be added, which is reviewed by at least one other member.

- A task is finished when the program still compiles, the matching tests of the test list pass, errors are displayed properly, and the work has been added to the shared version.

- Order to respect: Aaron's classes are needed by everybody (week 1), Wacim's database operations are needed by Camille, and Sacha's building blocks are needed by Camille before she can build her two screens.

- The file holding the database password stays on each member's computer and is never put on GitHub; an example file is shared instead.

- Blocked for more than 24 hours: say so in the group channel. Wacim either moves the task or puts two members on it, rather than letting the sprint slip.